## Sheet1
Online Leave Management System
Risk Management Register
Risk ID | Risk Description | Probability of Occurrence | Priority | Loss Size (Days) | Risk Exposure (Days) | Mitigation Response
RID 1 | Insufficient QA time to validate on all browsers and OS types. | 0.45 | 1 | 6 | 2.7 | Try to incorporate validity checks after every milestone, so that QA can be completed within available time.
RID 2 | Lack of verifiable sample data may affect the ability of the primary external stakeholder to validate end product. | 0.35 | 2 | 18 | 6.3 | Request Customer to provide sample data. If it is not possible from their end have the Database Management team create sample data and get it signed off by the customer.
RID 3 | Inadequate staff available from external stakeholders until very late in cycle. | 0.25 | 3 | 7 | 1.8 | Have a contingency team, with the necessary skill set, who could fill in the gaps as and when required.
RID 4 | Following end-user testing, more effort on the user guide may be necessary. | 0.25 | 3 | 18 | 4.5 | Could be handled by the Implementation and Technical Writing teams, jointly.
RID 5 | Backup and restore requires 3rd-party solutions (not evaluated yet). | 0.2 | 4 | 12 | 2.4 | Yet to be decided after discussions with the customer.
RID 6 | Insufficient time for external stakeholders to submit feedback on layout and composition of reports. | 0.1 | 5 | 5 | 0.5 | Have the Technical Writing and Quality Assurance teams validate the same.